## Project Status
[7 empty] | Status Key: | Planning
On track
At Risk
Delayed
Not Started
Complete
| Project Title | HFE POC | Proposal Complete Date | Proposal Acceptance Date | Study Plan Complete Date | Report Complete Date | Debrief/AAR Complete Date | Status | Notes
Discovery Research | Psychotherapy Project | Janey Barnes/ Kyle Maddox | 2019-12-24 | 2019-12-24 | Iterating Plan |  |  | On track | We got behind after the Nashville F2F but are moving forward with initial prototypes created to represent the requirements. Highest risk is decision is needed on which patient data collection options will be used e.g., eScreen, BHL, MHA, paper, etc.

## DERAIL
DERAIL (Decisions, Expectations (with assumptions), Risks, Actions, Issues Log)
Type (DERAIL) | Title | Status: Open, Closed | Who Identified | Action Owner | Date Opened | Target Close Date | Date Closed | Assumptions | Dependencies | Notes [add incremental notes, date/stamp, and Risk Prob (low, medium, high) and Impact (low, medium, high)] | Next Step(s): | Resolution Summary Notes (Accept, Mitigate, Transfer, Avoid)
Risk | patient data collection option | Open | Core Team | Dr. Crowe/Kyle Maddox | 2020-02-01 | TBD |  |  |  | Highest risk is decision is needed on which patient data collection options will be used e.g., eScreen, BHL, MHA, paper, etc. | Dr. Crowe is participating in demos of each option

## Project Team Members
Organization | Name | Function/Title | Core Project Team Y/N | Decision Maker, Influencer, Interested | Phone | Email | Project counterpart | Notes
| Dr. Crowe | Leadership | Y
| Michelle Ohmer | Leadership | Y
| Dr. Lindley | Pilot site lead (Palo Alto) | Y
| Ross Speir | Leadership/Human Factors | Y
| Kyle Maddox | Human Factors | Y
| Janey Barnes | Human Factors | Y
| Tom Cona | Human Factors | Y
| Dr. Kumpula | Clinical Lead- Patient facing Tool | Y
| Kas Adams | Designer CPRS Tool | Y
| Dr. Lindley | Clinical Lead - CPRS Tool | Y
| Dr. Gabrielle | Clinical Lead - CDS Tool | Y
| Russ Beebe | Designer CDS Tool | Y

## Operations
[5 empty] | Status Key: | On track
At Risk
Delayed
Complete
Activity | Purpose/Objective | Responsible | Support | Target Date | Complete Date | Status | Notes
Requirements for Patient Generated Data Tool | Show and tell with low fidelity prototype based on Patient Generated Data Tool Requirements | Janey Barnes/ Kyle Maddox | Patient Generated Data SubTeam | 2020-03-02 |  | At Risk | The patient data collection piece needs a decision about which option – eScreen, BHL, MHA, paper documents, etc),
Requirements for CPRS Tool | Show and tell with low fidelity prototype based on CPRS Tool Requirements | Kyle Maddox / Kas Adams | In-Session SubTeam | 2020-03-02 |  | On track | Kyle completed the wireframe and sent to the HF team for quick review. This fist pass wireframe is supposed to mockup all the requirements we’ve gathered for the reminder dialog (attached) to this point and mimic the workflow with the template. We limited the content to the ‘depression’ condition as per our earlier discussions to align with the MVP. We plan on reviewing this during our team call Thursday 2/27/2020 March 5, 2020 (changed to accomodate Dr. Crowe). Likely sub-teams or designer/HF will have calls to move the designs forward. Can include Dr. Crowe, Dr. Lindley and Dr. Kumpala based on availability.
Requirements for CPRS Tool | Show and tell with low fidelity prototype based on CDS Tool Requirements | Janey Barnes/ Russ Beebe | CDS SubTeam | 2020-03-02 |  | On track | Russ is developing wireframes based on the requirements. In parallel the HF team is reviewing "as we go". This first pass wireframes mockup the requrements we've gathered. We plan on review this during our team call Thursday 2/27/2020 March 5, 2020 (changed to accomodate Dr. Crowe). Likely sub-teams or designer/HF will have calls to move the designs forward. Can include Dr. Crowe, Dr. Lindley and Dr. Kumpala based on availability.
Usability Assessment 1 | Plan and execute User Feedback via Skype with core team and potential end users who are not part of the core team | Janey Barnes/ Kyle Maddox | Tom Cona | March 3 - March 16, 2020 |  | On track
Rapid prototyping iteration based on Usability Assessment 1 | Updates to each prototype based on Usability Assessment 1 | Kyle Maddox / Kas Adams (CPRS Tool) Russ Beebe / Janey Barnes (CDS Tool) | Tom Cona | March 3 - March 16< 2020 |  | On track
Usabability Assessment 2 | Plan and execute User Feedback (in person or via Skype) with up potential end users who are not part of the core team. | Janey Barnes/ Kyle Maddox | Tom Cona | March 17 - March 24< 2020 |  | On track
Rapid prototyping iteration based on Usability Assessment 2 | Updates to each prototype based on Usability Assessment 1 | Kyle Maddox / Kas Adams (CPRS Tool) Russ Beebe / Janey Barnes (CDS Tool) | Tom Cona | March 3 - March 16, 2020 |  | On track
Finalize build kits for each app | Finalize materials to inform Pilot Site CACs with requirements for building the Tools | All hands on deck |  | March 25 - March 31, 2020 |  | On track

## Communication
[7 empty] | Status Key: | On track
At Risk
Delayed
Complete
Campaign | Communication Activity | Purpose/Objective | Key Message | To (Audience) | From (delivered by) | Target Release Date | Communication Channel | Status | Notes

## Dropdown options (hidden)
Derail Options
Decision
Expectation
Risk
Action
Issue Log
Status
Open
Closed